## Task_Tracker
Workstream | Task ID | Task | Phase | Owner | Priority | Due Date | Dependency | Status | Risk | Notes | Next_Due_Date | Last_Auto_Update
Identity Security & MFA Enablement | SEC-001 | Identify MFA pilot user group | Planning & Pilot | IT Security Team | High | 2026-06-27 |  | Done | Medium |  | 2026-06-27
Identity Security & MFA Enablement | SEC-002 | Validate SSO compatibility | Planning & Pilot | IT Security Team | High | 2026-06-04 |  | Done | Medium |  | 2026-06-04
Identity Security & MFA Enablement | SEC-003 | Define MFA exception process | Planning & Pilot | IT Security Team | High | 2026-06-01 |  | Review | Medium |  | 2026-06-01
Identity Security & MFA Enablement | SEC-004 | Draft employee MFA communications | Planning & Pilot | PMO / Governance Support | High | 2026-06-07 |  | In Progress | Medium |  | 2026-06-07
Identity Security & MFA Enablement | SEC-005 | Configure MFA pilot environment | Planning & Pilot | IT Security Team | High | 2026-06-11 |  | In Progress | Medium | Pilot deployment delayed pending SSO validation | 2026-06-11
Identity Security & MFA Enablement | SEC-006 | Launch MFA pilot deployment | Rollout & Adoption | IT Security Team | High | 2026-07-06 | SEC-002, SEC-005 | Blocked | High |  | 2026-07-06
Identity Security & MFA Enablement | SEC-007 | Resolve pilot user issues | Rollout & Adoption | Help Desk Lead | High | 2026-09-04 | SEC-006 | To Do | Medium |  | 2026-09-04
Identity Security & MFA Enablement | SEC-008 | Evaluate pilot adoption metrics | Rollout & Adoption | Security Transformation Lead | High | 2026-07-10 | SEC-006 | To Do | Medium |  | 2026-07-10
Identity Security & MFA Enablement | SEC-009 | Prepare phased enterprise rollout | Rollout & Adoption | Security Transformation Lead | High | 2026-08-23 | SEC-008 | To Do | Medium |  | 2026-08-23
Identity Security & MFA Enablement | SEC-010 | Launch organization-wide MFA deployment | Rollout & Adoption | Security Transformation Lead | High | 2026-07-09 | SEC-008, SEC-009 | To Do | Medium |  | 2026-07-09
Security Awareness & Human Risk Reduction | SEC-011 | Assess existing security training content | Planning & Pilot | HR & Training Team | Medium | 2026-06-11 |  | In Progress | Medium |  | 2026-06-11
Security Awareness & Human Risk Reduction | SEC-012 | Select phishing-awareness training modules | Planning & Pilot | HR & Training Team | Medium | 2026-06-24 |  | To Do | Medium |  | 2026-06-24
Security Awareness & Human Risk Reduction | SEC-013 | Configure LMS training content | Planning & Pilot | HR & Training Team | Medium | 2026-06-21 | SEC-012 | In Progress | Medium |  | 2026-06-21
Security Awareness & Human Risk Reduction | SEC-014 | Design phishing simulation campaign | Planning & Pilot | IT Security Team | Medium | 2026-06-24 | SEC-012 | Review | Medium | Awaiting phishing simulation approval | 2026-06-24
Security Awareness & Human Risk Reduction | SEC-015 | Pilot phishing-awareness training | Planning & Pilot | HR & Training Team | Medium | 2026-06-24 | SEC-013, SEC-014 | Blocked | Medium |  | 2026-06-24
Security Awareness & Human Risk Reduction | SEC-016 | Launch mandatory employee training | Rollout & Adoption | HR & Training Team | High | 2026-08-07 | SEC-013, SEC-015 | Blocked | High | LMS content configuration required before launch | 2026-08-07
Security Awareness & Human Risk Reduction | SEC-017 | Monitor completion rates by department | Rollout & Adoption | PMO / Governance Support | Medium | 2026-09-08 | SEC-016 | In Progress | Medium | Department completion reporting in pilot phase | 2026-09-08
Security Awareness & Human Risk Reduction | SEC-018 | Send training reminder communications | Rollout & Adoption | HR & Training Team | Low | 2026-09-05 |  | In Progress | Medium | supportive, not mission-critical | 2026-09-05
Security Awareness & Human Risk Reduction | SEC-019 | Evaluate phishing simulation results | Rollout & Adoption | Security Transformation Lead | Medium | 2026-09-12 |  | To Do | Medium |  | 2026-09-12
Security Awareness & Human Risk Reduction | SEC-020 | Recommend targeted retraining groups | Rollout & Adoption | HR & Training Team | Low | 2026-07-06 |  | To Do | Medium | optimization task | 2026-07-06
Policy Compliance & Governance | SEC-021 | Review existing cybersecurity policies | Planning & Pilot | PMO / Governance Support | Medium | 2026-06-05 |  | Done | Medium |  | 2026-06-05
Policy Compliance & Governance | SEC-022 | Update acceptable-use policy | Planning & Pilot | PMO / Governance Support | Medium | 2026-06-20 | SEC-021 | In Progress | Medium |  | 2026-06-20
Policy Compliance & Governance | SEC-023 | Revise password and credential standards | Planning & Pilot | IT Security Team | Medium | 2026-06-21 | SEC-021 | In Progress | Medium |  | 2026-06-21
Policy Compliance & Governance | SEC-024 | Configure employee acknowledgment workflow | Planning & Pilot | PMO / Governance Support | Medium | 2026-06-27 | SEC-022, SEC-023 | In Progress | Medium |  | 2026-06-27
Policy Compliance & Governance | SEC-025 | Launch policy attestation campaign | Rollout & Adoption | PMO / Governance Support | High | 2026-07-25 | SEC-022, SEC-023, SEC-024 | To Do | High | Executive approval required prior to launch | 2026-07-25
Policy Compliance & Governance | SEC-026 | Monitor policy completion compliance | Rollout & Adoption | Department Managers | Low | 2026-07-25 | SEC-025 | To Do | Medium | monitoring function | 2026-07-25
Incident Intake & Escalation Modernization | SEC-027 | Document current incident reporting workflow | Planning & Pilot | IT Security Team | Medium | 2026-06-09 |  | In Progress | Medium |  | 2026-06-09
Incident Intake & Escalation Modernization | SEC-028 | Identify reporting bottlenecks | Planning & Pilot | IT Security Team | Low | 2026-06-20 |  | To Do | Medium | diagnostic work | 2026-06-20
Incident Intake & Escalation Modernization | SEC-029 | Design revised escalation process | Planning & Pilot | IT Security Team | Medium | 2026-06-20 | SEC-027, SEC-028 | In Progress | Medium |  | 2026-06-20
Incident Intake & Escalation Modernization | SEC-030 | Develop incident reporting templates | Planning & Pilot | IT Security Team | Medium | 2026-06-22 | SEC-029 | Review | Medium |  | 2026-06-22
Incident Intake & Escalation Modernization | SEC-031 | Train managers on escalation procedures | Rollout & Adoption | Department Managers | Medium | 2026-09-05 | SEC-029, SEC-030 | To Do | Medium |  | 2026-09-05
Incident Intake & Escalation Modernization | SEC-032 | Launch updated reporting process | Rollout & Adoption | Security Transformation Lead | High | 2026-08-25 | SEC-029, SEC-030, SEC-031 | In Progress | High | Manager training completion required before launch | 2026-08-25
Stakeholder Engagement & Change Management | SEC-033 | Identify stakeholder groups | Planning & Pilot | PMO / Governance Support | Medium | 2026-06-11 |  | Review | Low |  | 2026-06-11
Stakeholder Engagement & Change Management | SEC-034 | Develop communication strategy | Planning & Pilot | PMO / Governance Support | Medium | 2026-06-17 | SEC-033 | In Progress | Low |  | 2026-06-17
Stakeholder Engagement & Change Management | SEC-035 | Draft executive kickoff briefing | Planning & Pilot | PMO / Governance Support | Low | 2026-06-25 | SEC-034 | To Do | Low | helpful but non-blocking | 2026-06-25
Stakeholder Engagement & Change Management | SEC-036 | Publish employee FAQ document | Rollout & Adoption | PMO / Governance Support | Low | 2026-07-16 | SEC-034 | To Do | Low | change management support | 2026-07-16
Stakeholder Engagement & Change Management | SEC-037 | Conduct biweekly stakeholder reviews | Rollout & Adoption | PMO / Governance Support | Medium | 2026-09-13 | SEC-035 | Review | Low |  | 2026-09-13
Stakeholder Engagement & Change Management | SEC-038 | Coordinate adoption feedback sessions | Rollout & Adoption | Department Managers | Low | 2026-07-27 | SEC-036 | To Do | Low | refinement | 2026-07-27
Program Reporting & Delivery Governance | SEC-039 | Establish weekly reporting cadence | Planning & Pilot | PMO / Governance Support | High | 2026-06-20 |  | In Progress | Low |  | 2026-06-20
Program Reporting & Delivery Governance | SEC-040 | Build RAID log template | Planning & Pilot | PMO / Governance Support | High | 2026-06-07 | SEC-039 | In Progress | Low |  | 2026-06-07
Program Reporting & Delivery Governance | SEC-041 | Create executive status report template | Planning & Pilot | PMO / Governance Support | High | 2026-06-19 | SEC-039, SEC-040 | In Progress | Low | Executive template under stakeholder review | 2026-06-19
Program Reporting & Delivery Governance | SEC-042 | Establish milestone tracking framework | Planning & Pilot | PMO / Governance Support | High | 2026-06-04 | SEC-040 | In Progress | Low |  | 2026-06-04
Program Reporting & Delivery Governance | SEC-043 | Conduct weekly program status review | Rollout & Adoption | Security Transformation Lead | High | 2026-08-01 | SEC-041, SEC-042 | To Do | Low |  | 2026-08-01
Program Reporting & Delivery Governance | SEC-044 | Compile monthly executive updates | Stabilization & Reporting | Security Transformation Lead | Low | 2026-09-25 | SEC-043 | To Do | Low | ongoing reporting rather than delivery-critical | 2026-09-25 | 2026-05-22

## Timeline
A | B | C | D | E | F | G | H | Archived Formula Logic
Phase | Start Date | End Date | ToDo Days | InProgress Days | Review Days | Blocked Days | Auto_Update | #ERROR!
Planning & Pilot | 2026-06-01 | 2026-06-28 | 14 | 10 | 5 | 7 | TRUE | D2="Planning & Pilot",DATE(2026,6,1)+RANDBETWEEN(0,27),
Rollout & Adoption | 2026-06-29 | 2026-09-20 | 21 | 14 | 7 | 10 | TRUE | D2="Rollout & Adoption",DATE(2026,6,29)+RANDBETWEEN(0,83),
Stabilization & Reporting | 2026-09-21 | 2026-11-15 | 30 | 21 | 7 | 14 | TRUE | D2="Stabilization & Reporting",DATE(2026,9,21)+RANDBETWEEN(0,55)
)

## Rules
Task ID | Owner | Priority | Status | Risk | Dependency
SEC-001 | IT Security Team | High | Done | Medium
SEC-002 | IT Security Team | High | Done | Medium
SEC-003 | IT Security Team | High | To Do | Medium
SEC-004 | PMO / Governance Support | High | In Progress | Medium
SEC-005 | IT Security Team | High | To Do | Medium
SEC-006 | IT Security Team | High | Blocked | High | SEC-002, SEC-005
SEC-007 | Help Desk Lead | High | To Do | Medium | SEC-006
SEC-008 | Security Transformation Lead | High | To Do | Medium | SEC-006
SEC-009 | Security Transformation Lead | High | To Do | Medium | SEC-008
SEC-010 | Security Transformation Lead | High | To Do | Medium | SEC-008, SEC-009
SEC-011 | HR & Training Team | Medium | Done | Medium
SEC-012 | HR & Training Team | Medium | To Do | Medium
SEC-013 | HR & Training Team | Medium | In Progress | Medium | SEC-012
SEC-014 | IT Security Team | Medium | Review | Medium | SEC-012
SEC-015 | HR & Training Team | Medium | To Do | Medium | SEC-013, SEC-014
SEC-016 | HR & Training Team | High | Blocked | High | SEC-013, SEC-015
SEC-017 | PMO / Governance Support | Medium | To Do | Medium | SEC-016
SEC-018 | HR & Training Team | Medium | To Do | Medium
SEC-019 | Security Transformation Lead | Medium | To Do | Medium
SEC-020 | HR & Training Team | Medium | To Do | Medium
SEC-021 | PMO / Governance Support | Medium | Done | Medium
SEC-022 | PMO / Governance Support | Medium | In Progress | Medium | SEC-021
SEC-023 | IT Security Team | Medium | Review | Medium | SEC-021
SEC-024 | PMO / Governance Support | Medium | To Do | Medium | SEC-022, SEC-023
SEC-025 | PMO / Governance Support | High | To Do | High | SEC-022, SEC-023, SEC-024
SEC-026 | Department Managers | Medium | To Do | Medium | SEC-025
SEC-027 | IT Security Team | Medium | To Do | Medium
SEC-028 | IT Security Team | Medium | To Do | Medium
SEC-029 | IT Security Team | Medium | In Progress | Medium | SEC-027, SEC-028
SEC-030 | IT Security Team | Medium | Review | Medium | SEC-029
SEC-031 | Department Managers | Medium | To Do | Medium | SEC-029, SEC-030
SEC-032 | Security Transformation Lead | High | Blocked | High | SEC-029, SEC-030, SEC-031
SEC-033 | PMO / Governance Support | Medium | Done | Low
SEC-034 | PMO / Governance Support | Medium | In Progress | Low | SEC-033
SEC-035 | PMO / Governance Support | Medium | To Do | Low | SEC-034
SEC-036 | PMO / Governance Support | Medium | To Do | Low | SEC-034
SEC-037 | PMO / Governance Support | Medium | To Do | Low | SEC-035
SEC-038 | Department Managers | Medium | To Do | Low | SEC-036
SEC-039 | PMO / Governance Support | High | Done | Low
SEC-040 | PMO / Governance Support | High | To Do | Low | SEC-039
SEC-041 | PMO / Governance Support | High | In Progress | Low | SEC-039, SEC-040
SEC-042 | PMO / Governance Support | High | To Do | Low | SEC-040
SEC-043 | Security Transformation Lead | High | To Do | Low | SEC-041, SEC-042
SEC-044 | Security Transformation Lead | High | To Do | Low | SEC-043

## RAID_Log
RAID ID | Type | Description | Impact | Probability | Owner | Action | Status
RAID-001 | Risk | MFA pilot deployment delay due to unresolved prerequisite tasks (SEC-002, SEC-005) | High | Medium | IT Security Team | Complete SSO validation and finalize MFA environment configuration before deployment | Open
RAID-002 | Risk | LMS configuration delay may impact phishing-awareness rollout timeline (SEC-013, SEC-015) | High | Medium | HR & Training Team | Finalize LMS setup and validate training content before launch | Open
RAID-003 | Risk | Executive approval delay may postpone policy attestation campaign (SEC-025) | High | Medium | PMO / Governance Support | Secure stakeholder review and executive sign-off prior to launch | Monitoring
RAID-004 | Risk | Low employee participation may reduce effectiveness of phishing training programme | Medium | Medium | HR & Training Team | Implement reminder communications and manager escalation support | Monitoring
RAID-005 | Risk | Resistance to MFA adoption may reduce rollout effectiveness | Medium | Low | Security Transformation Lead | Develop communications strategy and user support materials | Monitoring
RAID-006 | Assumption | Existing cybersecurity policies can be revised without major regulatory conflict | Medium | Low | PMO / Governance Support | Validate compliance assumptions during policy review | Mitigated
RAID-007 | Assumption | Department managers will support escalation and training enforcement | Medium | Medium | Department Managers | Confirm stakeholder participation expectations during rollout | Open
RAID-008 | Assumption | Existing reporting systems can support new reporting cadence | Low | Low | PMO / Governance Support | Validate reporting templates during pilot reporting cycle | Mitigated
RAID-009 | Issue | MFA pilot deployment currently blocked pending prerequisite completion (SEC-006) | High | High | IT Security Team | Resolve SEC-002 and SEC-005 dependencies | Open
RAID-010 | Issue | Mandatory employee training launch blocked by incomplete LMS readiness (SEC-016) | High | High | HR & Training Team | Finalize SEC-013 and SEC-015 deliverables | Open
RAID-011 | Issue | Updated reporting process blocked pending manager escalation training (SEC-032) | Medium | Medium | Security Transformation Lead | Complete manager training and reporting templates | Open
RAID-012 | Dependency | Organization-wide MFA rollout dependent on pilot adoption success metrics (SEC-008, SEC-009) | High | Medium | Security Transformation Lead | Validate pilot results before enterprise rollout | Monitoring
RAID-013 | Issue | Initial cybersecurity policy baseline assessment completed (SEC-021) | Medium | Low | PMO / Governance Support | No further action required; incorporated into policy revision workstream | Closed
RAID-014 | Dependency | Security training content assessment completed to support awareness programme rollout (SEC-011) | Low | Low | HR & Training Team | Transition outputs into phishing-awareness module development | Closed
RAID-015
RAID-016
RAID-017
RAID-018
RAID-019
RAID-020
RAID-021
RAID-022
RAID-023
RAID-024
RAID-025
RAID-026
RAID-027
RAID-028
RAID-029
RAID-030
RAID-031
RAID-032
RAID-033
RAID-034
RAID-035
RAID-036
RAID-037
RAID-038
RAID-039
RAID-040
RAID-041
RAID-042
RAID-043
RAID-044
RAID-045
RAID-046
RAID-047
RAID-048
RAID-049
RAID-050
RAID-051
RAID-052
RAID-053
RAID-054
RAID-055
RAID-056
RAID-057
RAID-058
RAID-059
RAID-060
RAID-061
RAID-062
RAID-063
RAID-064
RAID-065
RAID-066
RAID-067
RAID-068
RAID-069
RAID-070
RAID-071
RAID-072
RAID-073
RAID-074
RAID-075
RAID-076
RAID-077
RAID-078
RAID-079
RAID-080
RAID-081
RAID-082
RAID-083
RAID-084
RAID-085
RAID-086
RAID-087
RAID-088
RAID-089
RAID-090
RAID-091
RAID-092
RAID-093
RAID-094
RAID-095
RAID-096
RAID-097
RAID-098
RAID-099